Work Packages for the CPC 2026:

WP1: Paradigm

Description: Implement a paradigm for MI tasks: right-, left hand, feet using PsychoPy.

Deadline:

Team members: Vitalik, Paul

Status: Done

Comments:

WP2: EEG Data Acquisition

Description: Record multiple sessions for current MI tasks (right/left hand, feet) of abled participant using LabRecorder. Ensure correct event labeling for epoch extraction later.

Create script for: loading raw EEG data  extracting event timestamps

Deadline:

Team members: Vitalik, Paul, Janniella

Recorded sessions: 23.06.2026, 07.07.2026

Status: Done

Comments:

WP3: Signal Pre-Processing & Artifact Removal

Description:

An example of a typical pre-processing for MI includes

1. Bandpass filtering to focus on 8-30 Hz (to include mu and beta frequency) (e.g. 0.5-50 Hz),

2. Notch filtering,

3. Re-referencing methods Laplace/CAR (check behavior over C3/Cz/C4 specifically)

Artifact removal includes

1. ICA  (offline baseline)

2. Possible epoch rejection

think about which pre-processing/artifact removal methods can be transferred from offline to online.

Deadline:

Team members: Paul, Vitalik

Status: Ongoing

Comments:

WP4: Feature Extraction & Spatial Filtering

identify optimal EEG features for MI classification

Suggestions:

1. Baseline features: mu & beta rhythm.

2. Spatial filtering: Common Spatial Patterns (CSP)

3. Explore MNE feature extraction

4. Frequency-domain features: PSD, ERD/S

Compare feature extraction methods for best discrimination.

Deadline:

Team members: Micha

Status: Ongoing

Comments:

WP5: Classification & Evaluation

develop MI classification model based on extracted features

Suggestions:

1. Implement baseline classifiers such as LDA, sLDA, SVM, etc.

2. Cross-validation

3. Evaluation: Accuracy, F1-score, Confusion matrix, …

since we are using the same subject for the game, we prioritize subject-specific calibration.

Deadline:

Team members: Sebastian, Paul

Status: Ongoing

Comments:

WP6: Online connection

the idea is, that we want real-time EEG processing (LSL input stream  online pre-processing  feature extraction  classification output) with classifier feedback (prediction output, confidence estimation)

Discuss acceptable latency, window length vs classification accuracy trade-off.

Details to be discussed.

Deadline:

Team members: Vitalii

Status: Ongoing

Comments: